LRP Rural Framework Action Plan 2022-2030

Using the priorities identified in the Rural Framework, the following action plan has been produced. The plan highlights in blue the actions from the LRP Rural Framework and then lists current activity which best fits each of the priorities, together with progress to date.

Most of the actions identified in the LRP Rural Framework, involve keeping a watching brief on new policies and funding streams as they emerge, to support the economy post-covid and the LRP needs to ensure that due consideration is given to rural areas, as these policies come forward.

In determining priorities for action, a number of factors have been taken into account:

• responding to immediate and emerging priorities where resources have been identified;

• consideration of additional impact arising from EU Transition;

• importance of addressing the most adversely covid affected parts of the economy, but also of building upon strengths of the area to aid recovery;

• ensuring that any actions address the needs of all parts of our rural economy, be that rural, high street or village centre; and that where possible actions will have a wide-ranging impact and

• ensuring the actions remain flexible to consider the impact of future lockdowns and closure of non-essential businesses

SUMMARY OF ACTIVITIES

Priority 1 Climate Change and the Environment

Action:The LRP need to keep abreast of policies in this area, including Leicestershire County Council Environment Strategy, in order that we can maximise any opportunities to influence priorities/ lead on any future funding streams that arise to promote green growth.

This is a cross- cutting theme that needs to be considered across all the priorities, as new businesses emerge in the green sector and old businesses change their behaviours, to reduce their carbon footprints.

Green BELLE- Run by Leicester City Council this Grant Programme provides grants for businesses to become green.

| Green BELLE Phase 1 (2017-2019) Grants Awarded in County: 50 Total Grant Amount Paid in County: £239,027.14 | Phase 1 Split by District: Blaby District Council £45,903.19 - 8 Grants Awarded Charnwood Borough Council £38,809.10 - 8 Grants Awarded Harborough District Council £48,531.55 - 10 Grants Awarded Hinckley & Bosworth Borough Council £27,849.40 - 7 Grants Awarded Melton Borough Council £18,563.10 - 5 Grants Awarded North West Leicestershire District Council £37,293.78 - 7 Grants Awarded Oadby & Wigston Borough Council £22,077.02 - 5 Grants Awarded Grand Total Paid in County £239,027.14 - 50 Grants Awarded |
| --- | --- |
| Green BELLE Phase 2 (2020-current) Grants Defrayed in County to Date: 32 Grants Agreed in County but not yet defrayed: 24 Total Grant Amount Paid in County to Date: £189,205.72 Total Grant Amount Allocated in County to Date: £324,464.67 | Phase 2 Split by District: Blaby District Council £88,629.58 - 14 Grants Allocated Charnwood Borough Council £55,748.27 - 9 Grants Allocated Harborough District Council £51,946.12 - 9 Grants Allocated Hinckley & Bosworth Borough Council - £63,574.28 - 11 Grants Allocated Melton Borough Council £1,665.00 - 1 Grants Allocated North West Leicestershire District Council £54,998.26 - 10 Grants Allocated Oadby & Wigston Borough Council £7,903.16 - 2 Grants Allocated Grand Total £324,464.67 - 56 Grants Allocated |
| Both Phases Totals Total Grants Defrayed in County to Date: 82 Total Grants Allocated in County to Date: 106 Total Grant Amount Paid in County to Date: £428,232.86 Total Grant Allocated in County to Date: £563,491.81 |  |

Waste Prevention Initiatives

Net Zero Roadmap – The County Council has launched a consultation on its NetZero Road map 4th May until 26th July

https://www.leicestershire.gov.uk/have-your-say/current-engagement/net-zero-strategy-and-action-plan-2045

Tree Replacement Scheme - https://www.leicestershire.gov.uk/environment-and-planning/conservation-and-sustainability/apply-for-trees/free-replacement-trees

Priority 2 – Rural inclusion and skills including supporting those furthest from the labour market move closer to work

Action- The LRP must keep a watching brief on any new funding streams that come forward, such as the UKSPF as the   potential huge rise in unemployment as the furlough schemes end may mean that there is a need for a specific fund for rural areas, which is targeted at all groups not just specific cohorts.

- There may be other specific support we should be looking at for rural areas based on evidence as it arises.

- The LRP in support of its partners, needs to champion specific agricultural issues regarding course content through the Skills Advisory Panel.

WiLL Project (Work Live Leicestershire) -To deliver support to assist people into employment, self-employment or training.

Targets:1019 total participants - £2.4 million ESF-Targets: 1019 total participants

Project extended until June 2023.

June 2022 update- Currently delivered 822 participants of which 415 were men, 404 were female and 3 were other gender status.

487 are unemployed and 335 are economically inactive £2.4 million ESF

Kickstart initiative to give young people placements for 6 months – Cohorts of 30 required. internal placements- extended to 12 months.

For Kickstart;

End May 20222 update 20 participants in the end (+ 1 who resigned after 1 month) -

4 still in 1st 6m period

9 have been extended to 12 months so continue to gain experience

1 relocated to get married

2 have departed (unable to further support/find suitable role)

4 have secured a f/t position with us

Overall, managers have found participants to be keen to learn and of value to the organisation.

Melton and NWLDC are working to promote East Midlands Chamber as intermediary, whereas HDC and HBBC are developing their own schemes.

Work Skills Leics based on Work Clubs in libraries will give 1-2-1 support for anyone looking to write a CV, improve interview and digital skills.

June  2022 update- 46 referrals, 86 received Information, Advice and Guidance, 30,840 sessions on web-site,31 referred to Go Learn and 57 people gone into employment.

Priority 3- Support small and micro businesses in rural areas to expand, diversify and grow.

Action- The LRP needs to carry out any initial preparation now to develop potential projects, to ensure we are in the best position when the UKSPF is open for applications

- If also need to examine what the potential criteria for such a scheme would be through identification of gaps and ensuring there is no duplication with schemes being run by partners such as the National Forest. Partners have already identified that increasing forest productivity is not relevant for all areas of the County.

Action – is there anything that the LRP needs to co-ordinate or influence with specific reference to Rural areas?

-	Is there any feedback from partners such as the FSB as to specific issues faced by businesses in Rural areas?

-	The LRP need to continue to work with the Growth Hub as the first port of call for business advice and notify them of any rural business issues.

East Leicestershire and Hinckley & Bosworth and North Warks LEADER programmes now Closed

EAFRD- Now closed

Growth Hub business support programme. Increase the number of rural businesses accessing ERDF business grants

Total grants available £1,890,000 capital £162,750 revenue=£2052750

Allocated £1,434,220.9

51 grants in county, 25 in city

Digital growth programme – now fully committed. Actual end Feb 2022- 1474businesses have engaged with 889 businesses receiving intensive support – 571 in the County and 318 in the city. 211 businesses have received a grant totalling £6 million

Priority 4 - Supporting sectors of importance to rural areas – Tourism, Food and Drink, Creative Industries and land based businesses

Action; LRP to examine whether it can influence/lead on any future funding to support these sectors and LRP to support partners in any plans they may have to aid recovery

Strategic Tourism- Tourism Advisory Board has played a key role in highlighting to the Govt issues arising as a result of lockdown as Tourism and Hospitality businesses especially affected, whilst still delivering against strategic tourism priorities.

Utilising LLEP Accelerator funding the “Uncover the Story” campaign has been delivered which involved key tourism attractions and areas of the county such as the National Forest and Market Towns producing unique selling points which will be utilised to attract visitors to the County via National Campaigns.

“Fitcation” campaign was launched on 15th June at Stoney Cove and has put together unique activities including e-bikes, archery, tank driving and watersports to attract a different audience. Led by PMO

Sustainable Food Strategy -5 ambitions including: Business networking linking producers, farms, schools and caterers.

- Working with Food and Drink Forum to identify handful of businesses to progress through a sustainability framework (includes health and carbon)

- Leicestershire Traded Services and wider LCC working with local farmers to identify routes to procurement and carbon/biodiversity benefits of doing so

- Allerton Project leading next tranche of work looking at Leicestershire Sustainable Farming and Food Chain work – to include NFU and Brooksby

- Continuing to work with Eco Village in Market Harborough to champion local produce, regenerative farming and community involvement

- Working on first Food Summit – to be held early April (invitation soon).

The food plan is much looser now – it doesn’t have an action plan, but we work with partners to identify areas of priority and how to progress these priority areas. The food charter is still there and the new officer (Catherine Turnell) will be looking at how to increase engagement and use the charter to help with this.

Manufacturing Zone Project Update

- Consultants identified two key areas within the borough which were deemed viable for Manufacturing Zone status (four site appraisals were conducted in total). These included the Leicester Gateway site and Crossfield Drive/Saxby Road site.

- MBC is continuing to engage with landowners, developers and agents to ensure future development of the sites, with the aim of attracting indigenous businesses and inward investors.

- Promotion of the sites has included within our Corporate website, Discover Melton website and within promotional material produced by Invest in Leicester.

Food Enterprise Centre Project (Food Technologist) Update

- 76 businesses currently on our database.

- 18 of which have received technical support and/or signposted within the past year.

- Currently, there are 2 technical briefs being produced with Feast and Furious and Vale Microgreens.

Priority 5 – Improve physical and digital connectivity in rural areas

Action- Continue to champion the need for improved coverage of superfast broadband in rural areas of Leicestershire.

Superfast Leicestershire -Broadband deployment to increase coverage to as close to 100% as possible. Phase 3 which covers the West of the County has now been implemented. Gigabit voucher scheme continues to be rolled out. The Programme is working on a series of Digital Hubs utilising public sector buildings. We will be undertaking a joint procurement with Warwickshire County Council for the remaining under-served properties to achieve the mass needed to attract a provider. Procurement to commence late 2022/early 2023.

On-line selling platforms- Loughborough BID, Melton BID , Market Harborough and Charnwood procured a town/district wide selling platform for retailers who didn’t sell on-line to assist businesses during the pandemic.This has proven more difficult than anticipated and Melton have yet to make any sales and the Charnwood contract has ended as it was paid for using “Welcome Back Funding” from the Govt.

Electric Car Clubs

A survey has been carried out with Parish Councils across the County and 20 Councils which equates to 11% of all Councils are interested in taking this forward, with 10 very keen to move forward. The  Parish Councils have to undertake a residents survey to ensure there is enough support for the club by residents. So far Ben Dodd from Green Fox Community Energy  Co-Operative has set up 4 online surveys and awaiting meetings/decisions on the other 16. The councils range in population from 600 up to 11,000, but are mostly one or two thousand. Parish councils  have responded from all districts/boroughs of Leicestershire apart from Oadby and Wigston. The most responses were from Blaby and Harborough.

What would a rural electric car club look like?  –  https://www.youtube.com/watch?v=VnfXMpXdD2k as an example of how it could work. The provision of an electric car club to villages has all sorts of cross cutting benefits, from tackling isolation through a volunteer driver scheme, to a reduction of CO2e and people giving up a second car, to provide transport where public transport is limited or non-existent, and helping economically at a time when the cost of living is really challenging. e.g. the cost to run a car per year is circa £3,300 (RAC) and will rise with the fuel increases.

Now at the stage where we need to fund a pilot study in different villages and capture learning to potentially roll it out across Leicestershire. However, it is not cheap to start, as the biggest barrier to do this is the capital cost of the electric car. If a pilot was carried out in 6 villages, the capital alone for the cars would be in the region of £180,000. So, although the need seems to be there, the next challenge is to secure the funding for the pilot. Ideally the business model would provide the electric car free of charge to the Parish Council, on the undertaking that it would be transferred to another Parish Council once the club is well established, therefore making the most of the cars.

Due to the funding required, a partnership is required, where Green Fox is a partner in a larger application for funds, or indeed identify a funding organisation that Green Fox could apply to individually for the support required. So far an application has been submitted- EOI to the Dept of Transport tackling loneliness through transport fund, and they have engaged the National Lottery for support. However other ways in which we could access funding to start the pilot now need to be sought.

Digital Skills Partnership – This has been set up by the LLEP and has an overall steering group which Mrs Sarah Rudkin Economic Growth Team Leader sits on and various sub-groups to look at low level interventions including getting hardware to disadvantaged groups and an Employer Group which is looking at feedback from businesses to understand the needs of their workforce. Mrs Helen Harris Economic Growth Manager sits on this group and can feed back to the group.

Priority 6 -Shaping local communities and places

Action; LRP to have regular agenda item on issues arising from Community/Voluntary sectors and assist partners as appropriate

Neighbourhood Planning – the latest position is as follows :

Rural Housing Enabler Project -Project has just been re-tendered for a year up to April 2022 and Midlands Housing were successful.

A project extension for 12 months is about TBC. Concentration has been on site finding in this new contract. £45,200 pa

(6 Districts, LCC and 3 x RSLs)

Support rural places of importance-

National Forest have recently launched their National Forest Design Guide launched 2021to encourage buildings to be more sustainable in the way they are built and this will be followed by the Heart of the Forest Masterplan.

Charnwood Forest- £2.9m in HLF funding and another approx. £0.9m in partner match funding, making the total project value £3.9m. Projects fall into 3 themes;

- Explore Charnwood

- Understand Charnwood

- Care for Charnwood

Some of the types of projects include:

- Improving rights of way and access to the forest

- Supporting sustainable travel solutions

- Community engagement and education activities

- Improving the tourism economy and visitor experience

- Exploring and education on the heritage of the forest

- Community arts projects

- Promoting and developing local foods and products

Here is a link to a summary of the project

https://www.nationalforest.org/sites/default/files/components/downloads/files/LPS%20prospectus%20%28Aug%202018%29_1.pdf

A lot of effort is being put into ensuring a legacy for the project and the forest after the HLF funding period. A main focus of this is an application to UNESCO to get Geopark status for Charnwood Forest in recognition of the rare geology and fossils in the area.

Some social media platforms have been launched about this with more details coming soon. See below:

https://m.facebook.com/CharnwoodForestGeopark/

https://www.instagram.com/charnwoodforestgeopark/?hl=en-gb

https://ne-np.facebook.com/CharnwoodForestGeopark/videos/bardon-hill-is-not-only-the-highest-point-in-leicestershire-but-also-full-of-geo/652253072843825/